# BAAGUPADU PROJECT CHARTER

### AI-Powered Personalized Mentoring Ecosystem

## Table of Contents

- Document Control & Executive Summary

- Project Purpose & Justification

- Project Objectives & Scope

- Project Approach & Methodology

- Project Organization

- Project Timeline & Milestones

- Budget & Resources

- Risk Management

- Success Criteria & KPIs

- Governance & Communication

- Approval Section

- Appendices

## SECTION 1: DOCUMENT CONTROL & EXECUTIVE SUMMARY

### 1.1 Document Control

| Field | Value |
| --- | --- |
| Document Title | Baagupadu Project Charter |
| Document ID | BGP-CHTR-001 |
| Version | 1.0 |
| Classification | Confidential / Internal Use Only |
| Distribution | Executive Board, Strategic Advisors, Project Leadership Team, Core Development Team, External Partners |
| Status | Pending Approval |
| Prepared By | Baagupadu Team |
| Document Owner | Project Vision Holder |
| Date Issued | June 18, 2026 |
| Review Schedule | Weekly (Every Saturday) |
| Next Review | July 2, 2026 |

### 1.2 Project Identification

| Field | Value |
| --- | --- |
| Project Name | Baagupadu |
| Project Sponsor | Executive Sponsor |
| Project Vision Holder | Project Vision Holder |
| Project Manager | Project Manager |
| Duration | 6 Months (24 Weeks) |
| Total Investment | $80,800 |
| Primary Deliverable | "Sahayam" AI Mentor — Gemini Gem MVP and Website MVP |
| Strategic Portfolio | AI & Digital Transformation Initiative |

### 1.3 Executive Summary

Baagupadu is an AI-powered personalized mentoring ecosystem designed to help individuals — particularly Gen Z and Millennials aged 16–30 — move past the "Information Paradox," where unlimited access to content paradoxically produces decision paralysis, shallow learning, and a lack of career clarity rather than confidence and direction.

At the center of the product is Sahayam, a conversational AI mentor with a deliberately engineered personality blend (40% Close Friend, 25% Mentor, 20% Curious Explorer, 10% Career Coach, 5% Storyteller). Sahayam guides users through a structured six-phase discovery journey — from initial trust-building through childhood, teenage, and adult life-stage exploration, culminating in synthesized insights and a personalized guidance plan. This approach replaces static personality quizzes and generic AI chat with long-term, pattern-based self-discovery and accountability.

This charter authorizes a 6-month roadmap structured around five non-negotiable milestones: a working Gemini Gem prototype (M1), completed user validation (M2), a live Website MVP (M3), a beta launch (M4), and public launch (M5).(needs evaluation) Total estimated investment across the program is **X**, supported by an 8-person core team, with a target of 1,000 active users and10,000 in revenue within Year 1, scaling toward 50,000 users and $1,000,000 in revenue by Year 3.

## SECTION 2: PROJECT PURPOSE & JUSTIFICATION

### 2.1 Problem Statement — The Career Clarity Crisis

Despite unprecedented access to educational content and career resources, Gen Z in India is experiencing a career clarity crisis that manifests as burnout, disengagement, and anxiety. This is not a character flaw — it is a structural failure

Key Research Findings:

| Metric | Finding | Source |
| --- | --- | --- |
| India workplace burnout rate | 59% of employees (ages 18-24 hardest hit) vs. global avg 20% | McKinsey Health Institute |
| Students with career counselling access | Only 10.4% of Classes 9-12 students have professional counselling | Bharat Career Aspirations Report 2025 (UN-backed, 21,000+ students) |
| Gen Z worried AI will replace their roles | 45% believe AI could replace them within 3-5 years | Great Place to Work India 2025 |
| Students without career role models | 53.5% reported no career role model (55.8% for free school meal eligible) | ISE Gen Z Careers Report (1,100+ survey responses) |
| Students stressed about future careers | 69% say thinking about future careers causes stress (73% for girls) | ISE Gen Z Careers Report |

#### The Root Cause

Students who enter careers through external pressure — family expectation, institutional prestige, or assumption of security — are far more likely to disengage early. When work does not align with identity, exhaustion becomes existential . Career counselling at 16 prevents the crisis at 25 .

### 2.2 Business Case — The Gap We Are Closing

| Metric | Current State | Target State | Source |
| --- | --- | --- | --- |
| Career counselling access (students) | 10.4% | 80%+ | Bharat Career Aspirations Report |
| Students with career role models | 46.5% have none | 80%+ | ISE Report |
| Gen Z with structured guidance | Limited | Accessible | Mentoria / ISE Research |

The Opportunity: Structured career counselling is not about telling young people what to do. It is about giving them self-knowledge and information to make their own determination before consequences accumulate . Students who go through structured aptitude mapping, interest assessment, and career exploration carry their choices with conviction and resilience

Target demographic indicators (ages 16–30):

- 80%+ feel overwhelmed by available learning and career resources

- 70%+ start setting goals but fail to complete them

- 65%+ lack clarity on their career direction

- 60%+ possess knowledge but cannot apply it effectively

### 2.3 Market Context & Opportunity

#### Global Career Guidance & Mentorship Platforms Market

According to Stratistics MRC, the global Career Guidance & Mentorship Platforms Market is valued at USD 3.01 billion in 2025 and is projected to reach USD 6.45 billion by 2032, growing at a CAGR of 11.5%.

### Key Growth Drivers

- Growing demand for personalized career guidance

- Adoption of AI-driven assessments, mentorship matching, and skill mapping

- Integration of career guidance platforms by corporations and universities to improve employability outcomes

### Regional Trends

The Asia-Pacific region is the fastest-growing market, driven by:

- Rapid smartphone adoption

- Increasing demand for career development services

- Government initiatives promoting digital literacy and workforce upskilling

### India Market Opportunity

India presents a significant growth opportunity, with an estimated 250 million individuals lacking access to personalized career guidance. Additionally, India's 600+ million youth population (under 35 years) creates a vast addressable market for AI-powered career guidance and mentorship platforms.

### Sources

- Stratistics MRC – Career Guidance & Mentorship Platforms Market Report
https://marketpublishers.com/report/services/recruitment/career-guidance-mentorship-platforms-market-strat.html

### 2.4 Competitive Landscape

| Competitor | Approach | Weakness | Baagupadu's Advantage |
| --- | --- | --- | --- |
| Personality Tests (e.g., 16Personalities) | Static, survey-based | No depth, generic output | Life-stage pattern recognition |
| AI Assistants (e.g., ChatGPT) | Answer-based | No memory, no accountability | Long-term, persistent mentorship |
| Online Courses (e.g., Coursera) | Content-based | No personalization | Personalized, adaptive guidance |
| Human Career Counselors | Human-based | Expensive, inaccessible at scale | Scalable and affordable |

Note: Coursera, Udemy, LinkedIn Learning, MentorCruise, CoachHub, and BetterUp are key players in the space .

### 2.5 Strategic Alignment

Baagupadu sits within the organization's broader AI & Digital Transformation portfolio, alongside other applied-AI initiatives. It extends the organization's track record of building AI-powered solutions for underserved engagement and accessibility gaps into the personal development and career-guidance domain, and is positioned as a foundation for a multi-module mentoring ecosystem beyond this initial release.

## SECTION 3: PROJECT OBJECTIVES & SCOPE

### 3.1 SMART Objectives

| # | Objective | Measure | Target Date |
| --- | --- | --- | --- |
| 1 | Deliver a working Gemini Gem prototype ("Nenu Evaru?") with zero critical bugs at internal sign-off | QA test report, M1 demo | Week 4 |
| 2 | Validate the Sahayam persona-building methodology with real users | 20+ users tested, satisfaction ≥4.0/5, completion rate ≥80% | Week 8 |
| 3 | Design, build, and deploy a functional Website MVP integrating chat, persona dashboard, and career guidance | Live URL, zero critical bugs at launch | Week 16 |
| 4 | Launch a controlled beta program | 50+ active beta users, API cost <$100/month, response time <3s | Week 18 |
| 5 | Execute public launch and establish early growth momentum | 100+ active users in first month; foundation for 1,000 users in Year 1 | Week 20 |

### 3.2 In-Scope

- Gemini Gem MVP — the "Nenu Evaru?" foundation module

- The full six-phase conversational discovery journey (Trust Building → Guidance Delivery)

- Design and engineering of the Sahayam AI mentor personality and system prompts

- Trait Framework, Persona Framework, and Career Framework development

- Website MVP: chat interface, persona dashboard, career guidance view, progress tracking

- Two rounds of structured user validation testing

- Controlled beta launch (50+ users) and subsequent public launch

- Core technology stack: Gemini API, React/Next.js frontend, Node.js/Python backend, PostgreSQL database

### 3.3 Out-of-Scope (proposed boundaries — pending confirmation by Project Vision Holder)

- Future modules: "Ekkadiki Vellali?" (Career Direction), "Ela Penchukovali?" (Skill Development), "Em Chesi?" (Life Planning) — reserved for the post-launch roadmap

- Native iOS/Android applications — this charter covers a web-first MVP only

- Multi-language support beyond the initial language set — future consideration

- Enterprise or B2B offerings — initial launch is consumer-focused

- Paid subscription tiers and monetization mechanics — to be scoped separately post-Year 1

### 3.4 Key Deliverables

| Deliverable | Linked Milestone | Owner |
| --- | --- | --- |
| Functional "Nenu Evaru?" Gemini Gem | M1 | Prompt Engineer |
| User Validation & Feedback Analysis Report | M2 | Project Manager |
| Live Website MVP | M3 | System Architect |
| Beta Launch & Monitoring Report | M4 | Project Manager |
| Public Launch & Marketing Campaign | M5 | Project Vision Holder |

## SECTION 4: PROJECT APPROACH & METHODOLOGY

### 4.1 Solution Overview

┌─────────────────────────────────────────────────────────────────┐


│                       Baagupadu ECOSYSTEM                       │


├─────────────────────────────────────────────────────────────────┤


│                                                                   │


│  📱 GEMINI GEM (Phase 1)                                          │


│      └── "Nenu Evaru?" — Foundation Module                       │


│                                                                   │


│  🌐 WEBSITE MVP (Phase 3)                                         │


│      ├── Full User Experience                                    │


│      ├── Persona Dashboard                                       │


│      ├── Career Guidance System                                  │


│      └── Progress Tracking                                       │


│                                                                   │


│  🔮 FUTURE MODULES (Post-Launch)                                  │


│      ├── "Ekkadiki Vellali?"   (Career Direction)                 │


│      ├── "Ela Penchukovali?"   (Skill Development)                │


│      └── "Em Chesi?"           (Life Planning)                    │


│                                                                   │


└─────────────────────────────────────────────────────────────────┘

### 4.2 The Six-Phase Journey

| Phase | Exchanges | Focus | Key Output |
| --- | --- | --- | --- |
| 1 — Trust Building | 3–5 | Warm welcome, psychological safety | User comfort, engagement |
| 2 — Childhood (0–12) | 8–12 | Family, curiosity, play, early patterns | Core emotional blueprint |
| 3 — Teenage (13–19) | 10–15 | Identity, friends, values, resilience | Social & values profile |
| 4 — Adult (20–30) | 8–12 | Career, skills, purpose, current state | Ambition & growth patterns |
| 5 — Synthesis | 5–8 | Pattern weaving, insight sharing | Comprehensive persona |
| 6 — Guidance Delivery | 5–10 | Career direction, action steps | Personalized roadmap |

Each phase builds on the prior one — the system intentionally avoids a "survey" feel by pacing the journey across short, conversational exchanges rather than a single long-form questionnaire.

### 4.3 Technology Stack

| Layer | Technology | Purpose | Monthly Cost |
| --- | --- | --- | --- |
| AI Platform | Google Gemini Gems | Hosts the AI mentor | $20–50 |
| Frontend | React / Next.js | User interface | $0–20 |
| Backend | Node.js / Python | API logic | $0–30 |
| Database | PostgreSQL | User data | $0–20 |
| Hosting | Vercel / AWS | Deployment | $10–30 |
| Monitoring | Custom analytics | Performance & usage | $5–10 |
| TOTAL |  |  | $40–150/month |

## SECTION 5: PROJECT ORGANIZATION

### 5.1 Team Composition

| Role | Count | Responsibility | Criticality |
| --- | --- | --- | --- |
| Project Vision Holder | 1 | Strategic direction, final decisions | Critical |
| AI Product Architect | 1 | Product design, persona framework | Critical |
| Prompt Engineer | 1 | System prompts, AI behavior | Critical |
| Conversational Designer | 1 | Question banks, conversation flow | High |
| Psychologist-Inspired UX Designer | 1 | Emotional intelligence, user psychology | High |
| Career Intelligence Architect | 1 | Career frameworks, guidance engine | High |
| System Architect | 1 | Technical architecture, implementation | Critical |
| Project Manager | 1 | Coordination, testing, communication | Critical |
| TOTAL | 8 |  |  |

### 5.2 Role Definitions

| Role | Abbrev. | Description | Key Deliverables |
| --- | --- | --- | --- |
| Project Vision Holder | PVH | Strategic direction, final decisions | Vision, approvals |
| Executive Sponsor | ES | Budget, resources, escalation | Budget approval |
| AI Product Architect | AIA | Product vision, persona framework | Product design |
| Prompt Engineer | PE | System prompts, AI behavior | Sahayam personality |
| Conversational Designer | CD | Question banks, conversation flow | UX flow |
| UX Designer | UX | Emotional intelligence, psychology | User experience |
| Career Architect | CA | Career frameworks, guidance | Career guidance |
| System Architect | SA | Technical architecture | Infrastructure |
| Project Manager | PM | Coordination, testing, communication | Timeline, reports |
| QA Lead | QA | Testing, validation | Quality assurance |

### 5.3 RACI Legend

| Symbol | Meaning | Description |
| --- | --- | --- |
| R | Responsible | Performs the work |
| A | Accountable | Ultimately answerable (only one per task) |
| C | Consulted | Input required before completion |
| I | Informed | Needs status updates |

### 5.4 RACI Matrix — Phase 1: Foundation

| Task | PVH | ES | AIA | PE | CD | UX | CA | SA | PM | QA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Vision & Charter | A | R | C | I | I | I | I | I | R | I |
| System Prompt Creation | I | I | C | R/A | C | C | I | I | I | I |
| Sahayam Personality Design | I | I | C | R/A | C | C | I | I | I | I |
| Childhood Questions | I | I | C | C | R/A | C | C | I | I | I |
| Teenage Questions | I | I | C | C | R/A | C | C | I | I | I |
| Adult Questions | I | I | C | C | R/A | C | C | I | I | I |
| Conversation Flow Design | I | I | C | C | C | R/A | I | I | I | I |
| Trait Framework | I | I | R/A | C | C | C | C | I | I | I |
| Persona Framework | I | I | R/A | C | C | C | C | I | I | I |
| Career Framework | I | I | C | C | C | C | R/A | I | I | I |
| Gemini Gem Creation | I | I | C | C | I | I | I | R/A | I | R |
| Initial Testing | I | I | C | C | C | C | I | C | R/A | R |

### 5.5 RACI Matrix — Phase 2: Validation

| Task | PVH | ES | AIA | PE | CD | UX | CA | SA | PM | QA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Test Plan Creation | I | I | C | I | C | C | I | I | R/A | R |
| User Recruitment (10–15) | C | I | C | I | C | C | I | I | R/A | I |
| Testing Execution — Round 1 | I | I | I | I | C | C | I | I | R/A | R |
| Feedback Collection | I | I | C | C | C | R/A | C | I | R | R |
| Feedback Analysis | I | I | R/A | C | C | C | C | C | R | R |
| System Refinements | I | I | C | R | R | R | C | C | I | C |
| Testing Execution — Round 2 | I | I | I | I | C | C | I | I | R/A | R |
| Validation Sign-off | R/A | C | C | I | I | I | I | I | R | C |

### 5.6 RACI Matrix — Phase 3: Website Development

| Task | PVH | ES | AIA | PE | CD | UX | CA | SA | PM | QA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| System Architecture | I | I | C | I | I | I | I | R/A | C | C |
| Database Design | I | I | C | I | I | I | I | R/A | I | C |
| API Development | I | I | C | I | I | I | I | R/A | I | C |
| Backend Development | I | I | C | I | I | I | I | R/A | I | C |
| Frontend Development | I | I | C | I | C | C | I | R/A | I | C |
| Integration | I | I | C | I | I | I | I | R/A | I | R |
| QA Testing | I | I | C | I | I | I | I | C | I | R/A |
| UAT Testing | I | I | C | I | C | C | I | C | R/A | R |
| Deployment | I | I | C | I | I | I | I | R/A | I | C |

### 5.7 Decision Rights Matrix

| Decision Type | Who Decides | Who Consults | Who Informs |
| --- | --- | --- | --- |
| Strategic Direction | Vision Holder | All | Project Manager |
| Budget & Resources | Executive Sponsor | Project Manager | All |
| Product Features | Product Architect | UX, Career Architect | Project Manager |
| Technical Architecture | System Architect | Product Architect | Project Manager |
| Personality & Prompts | Prompt Engineer | UX, Product Architect | Project Manager |
| User Experience | UX Designer | All | Project Manager |
| Career Frameworks | Career Architect | Product Architect | Project Manager |
| Timeline & Milestones | Project Manager | All | Vision Holder |
| Quality Standards | QA Lead | All | Project Manager |

## SECTION 6: PROJECT TIMELINE & MILESTONES

## 6.1 Guiding Philosophy: Speed & Focus

"A useful AI agent can launch on a lean stack if you keep the scope tight. One job, one user, and one short path to value beat a broad plan every time."

- Scope: Focus exclusively on the "Nenu Evaru?" Gemini Gem MVP.

- Team: Lean team of 2–3 core members.

- Tools: AI-assisted development using Claude Pro, Gemini, and open-source frameworks such as CrewAI and LangGraph.

- Goal: Deliver a functional, tested Gemini Gem within 6 weeks (1.5 months).

## 6.2 Six-Week Master Timeline

| Phase | Timeline | Activities | Deliverables |
| --- | --- | --- | --- |
| Foundation & Prompt Engineering | Weeks 1–2 | Define Sahayam personality, create system_prompt.md, develop question banks (childhood, teenage, adult), design trait/persona/career frameworks | Personality design, prompts, assessment framework |
| Gemini Gem Development | Weeks 3–4 | Gemini Gem setup, prompt integration, testing, internal QA, bug fixing | Functional Gemini Gem MVP |
| Validation & Launch | Weeks 5–6 | User testing (10–15 users), feedback analysis, refinements, final testing and deployment | Production-ready Gemini Gem |

### Detailed Timeline

| Days | Tasks |
| --- | --- |
| Day 1–3 | Define Sahayam personality and create system_prompt.md |
| Day 4–7 | Create question banks covering childhood, teenage, and adult experiences |
| Day 8–14 | Build trait, persona, and career recommendation frameworks |
| Day 15–18 | Configure and set up Gemini Gem |
| Day 19–21 | Integrate prompts and conduct initial testing |
| Day 22–28 | Internal testing, debugging, and refinements |
| Day 29–33 | User testing with 10–15 participants |
| Day 34–36 | Analyze feedback and improve the Gem |
| Day 37–42 | Final testing and public launch |

### Timeline Visualization

text

┌───────────────────────────────────────────────────────────┐


│                 6-WEEK LAUNCH TIMELINE                    │


├───────────────────────────────────────────────────────────┤


│                                                           │


│ WEEKS 1-2: FOUNDATION & PROMPT ENGINEERING                │


│ ├── Day 1-3   : Define Sahayam personality, system prompt  │


│ ├── Day 4-7   : Create question banks                     │


│ └── Day 8-14  : Build trait, persona & career frameworks  │


│                                                           │


│ WEEKS 3-4: GEMINI GEM DEVELOPMENT                         │


│ ├── Day 15-18 : Gemini Gem setup and configuration        │


│ ├── Day 19-21 : Prompt integration and testing            │


│ └── Day 22-28 : Internal testing and bug fixes            │


│                                                           │


│ WEEKS 5-6: VALIDATION & LAUNCH                            │


│ ├── Day 29-33 : User testing (10-15 users)                │


│ ├── Day 34-36 : Feedback analysis and refinements         │


│ └── Day 37-42 : Final testing and launch                  │


│                                                           │


└───────────────────────────────────────────────────────────┘

### 6.3 Phase Breakdown — Detailed Version

#### Phase 1: Foundation (Weeks 1–2)

Owner: Prompt Engineer + Conversational Designer
Priority: CRITICAL
Goal: Establish Sahayam's personality, create prompts, and design the conversational framework.

##### Week 1: Strategic Foundation & Prompt Engineering

| Day | Task | Owner | Deliverable | Success Criteria |
| --- | --- | --- | --- | --- |
| Day 1 | Define Sahayam's personality (40% Friend, 25% Mentor, 20% Explorer, 10% Coach, 5% Storyteller) | Prompt Engineer | Personality Framework v1.0 | Personality traits documented |
| Day 2 | Draft trust-building prompts (Phase 1) | Prompt Engineer | system_prompt.md | Warm opening exchanges designed |
| Day 3 | Draft childhood exploration prompts (Phase 2) | Prompt Engineer | Childhood prompts | 8–12 questions created |
| Day 4 | Draft teenage exploration prompts (Phase 3) | Prompt Engineer | Teenage prompts | 10–15 questions created |
| Day 5 | Draft adult exploration + synthesis (Phase 4–5) | Prompt Engineer | Adult + Synthesis prompts | Adult and synthesis questions created |
| Day 6 | Draft guidance delivery prompts (Phase 6) | Prompt Engineer | Guidance prompts | Guidance flow designed |
| Day 7 | Internal review and refinement | Prompt Engineer + AI Product Architect | system_prompt.md v1.0 | Personality consistency verified |

###### Key Decisions

| Decision | Rationale |
| --- | --- |
| Sahayam Personality Mix | Users prefer a trusted friend over a formal advisor |
| Six-Phase Journey | Clear progression and structured data collection |
| Conversational Approach | More engaging than surveys |
| Adaptive Personality | Different users require different tones |

###### Risks & Mitigation

| Risk | Mitigation |
| --- | --- |
| Prompt quality issues | Multiple iterations and user testing |
| Personality inconsistency | Personality Style Guide |
| Forced transitions | Natural transition prompts |

##### Week 2: Question Bank Development

Owner: Conversational Designer
Priority: CRITICAL

###### Childhood Questions (0–12 years)

| Focus Area | Questions | Deliverable |
| --- | --- | --- |
| Family & Emotional Security | 15 | childhood_questions.json v1 |
| Curiosity & Learning Patterns | 15 | childhood_questions.json v2 |
| Confidence, Social & Risk-taking | 15 | childhood_questions.json v3 |

Success Criteria

- 45+ childhood questions

- Non-boring conversational style

- Trait mapping for each question

- Follow-up prompts included

###### Teenage Questions (13–19 years)

| Focus Area | Questions | Deliverable |
| --- | --- | --- |
| Identity Formation & Social Dynamics | 15 | teenage_questions.json v1 |
| Academic Ambition & Resilience | 15 | teenage_questions.json v2 |
| Values & Decision-Making | 15 | teenage_questions.json v3 |

Success Criteria

- 45+ teenage questions

- Emotionally sensitive design

- Trait mapping

- Follow-up prompts for emotional responses

###### Adult Questions (20–30 years)

| Focus Area | Questions | Deliverable |
| --- | --- | --- |
| Career, Purpose, Growth & Vision | 15–20 | adult_questions.json v1 |

Success Criteria

- 15–20 adult questions

- Connect past patterns to present

- Career and identity trait mapping

- Smooth transition to synthesis phase

##### Phase 1 Deliverables

| Deliverable | Owner | Acceptance Criteria |
| --- | --- | --- |
| system_prompt.md v1.0 | Prompt Engineer | All 6 phases designed |
| childhood_questions.json | Conversational Designer | 45+ questions |
| teenage_questions.json | Conversational Designer | 45+ questions |
| adult_questions.json | Conversational Designer | 15+ questions |
| Personality Style Guide | UX Designer | Sahayam personality documented |
| Transition Language | Conversational Designer | Natural phase transitions |

###### Sign-Off Criteria

- All prompts reviewed by AI Product Architect

- Personality consistency verified

- Questions follow "non-boring" principle

- Question banks cover all phases

- Follow-up prompts designed

#### Phase 2: Gemini Gem Development (Weeks 3–4)

Owner: System Architect
Priority: CRITICAL

##### Week 3: Framework Development

| Day | Task | Deliverable |
| --- | --- | --- |
| Day 1 | Define trait categories | trait_framework.json v1 |
| Day 2 | Map indicators to traits | trait_framework.json v2 |
| Day 3 | Define persona archetypes | persona_framework.json v1 |
| Day 4 | Map traits to archetypes | persona_framework.json v2 |
| Day 5 | Define career clusters | career_framework.json v1 |
| Day 6 | Map archetypes to careers | career_framework.json v2 |
| Day 7 | Framework integration review | Integration Plan |

###### Key Decisions

- 5 Trait Categories:

  - Social

  - Learning

  - Emotional

  - Career

  - Identity

- 4 Persona Archetypes:

  - Explorer

  - Builder

  - Connector

  - Thinker

##### Week 4: Gemini Gem Creation & Integration

| Day | Task | Deliverable |
| --- | --- | --- |
| Day 1 | Gemini Gem Setup | Working Environment |
| Day 2 | System Prompt Integration | Integrated Gem |
| Day 3 | Question Bank Integration | All Questions Loaded |
| Day 4 | Framework Integration | Complete Gem |
| Day 5 | Internal Testing (Phases 1–3) | Test Results |
| Day 6 | Internal Testing (Phases 4–6) | Test Results |
| Day 7 | Bug Fixes | Gem v1.0 (M1 Ready) |

###### Acceptance Criteria

- All prompts integrated

- Question banks accessible

- Frameworks loaded

- No critical bugs

- Natural phase transitions

- Sahayam personality remains consistent

Milestone M1: ✅ Working Gemini Gem

#### Phase 3: Validation & Launch (Weeks 5–6)

Owner: Project Manager
Priority: CRITICAL

##### Week 5: User Testing

| Day | Task | Deliverable |
| --- | --- | --- |
| Day 1 | Create Test Plan | Test Plan |
| Day 2 | Recruit 10–15 Users | Tester List |
| Day 3 | Tester Onboarding | Briefing |
| Day 4 | Test Round 1 | Test Data |
| Day 5 | Test Round 2 | Test Data |
| Day 6 | Feedback Collection | Feedback Logs |
| Day 7 | Initial Analysis | Preliminary Analysis |

###### Test User Criteria

| Criteria | Details |
| --- | --- |
| Age | 16–30 |
| Education | High School to College |
| Career Stage | Student / Early Career |
| Diversity | Rural, Urban, Mixed Backgrounds |
| Sample Size | 10–15 Users |

##### Week 6: Refinement & Launch

| Day | Task | Deliverable |
| --- | --- | --- |
| Day 1 | Detailed Analysis | Analysis Report |
| Day 2 | Prompt Refinements | Updated Prompts |
| Day 3 | Question Refinements | Updated Question Banks |
| Day 4 | Framework Refinements | Updated Frameworks |
| Day 5 | Final Testing | Test Results |
| Day 6 | Final Refinements | Gem v2.0 |
| Day 7 | Launch | M2 Complete |

###### Launch Checklist

- All critical bugs fixed

- User satisfaction > 4.0 / 5

- All 6 phases operational

- Persona building functional

- Career guidance personalized

Milestone M2: ✅ Validation & Launch Complete

##### Resource Requirements

| Phase | Personnel | Total Hours |
| --- | --- | --- |
| Phase 1 | Prompt Engineer + Conversational Designer | 160 |
| Phase 2 | AI Product Architect + System Architect + Career Architect | 120 |
| Phase 3 | Project Manager + UX Designer + AI Product Architect | 120 |
| Total | ~2.5 FTE Average | 400 Hours |

## 6.4 Milestone Summary

| ID | Milestone | Target Date | Deliverable | Owner | Dependencies |
| --- | --- | --- | --- | --- | --- |
| M1 | Working Gemini Gem | Week 4 | Functional "Nenu Evaru?" Gemini Gem | System Architect | None |
| M2 | User Validation & Launch | Week 6 | Feedback Analysis Report + Final Gemini Gem | Project Manager | M1 |

## 6.5 Critical Path

text

Week 1-2: Foundation


├── System Prompt Design


└── Question Bank Development


 

        ↓


 

Week 3-4: Framework Development + Gemini Gem


├── Trait Framework


├── Persona Framework


├── Career Framework


├── Gemini Gem Integration


└── M1: Working Gemini Gem ✅


 

        ↓


 

Week 5-6: Validation & Launch


├── User Testing (10-15 users)


├── Feedback Analysis


├── Prompt & Framework Refinement


└── M2: Validation & Launch ✅

## 6.6 Resource Requirements by Phase

| Phase | Personnel Hours | Owner | Timeline |
| --- | --- | --- | --- |
| Phase 1 — Foundation | 80 hrs (40 + 40) | Prompt Engineer + Conversational Designer | Weeks 1–2 |
| Phase 2 — Gemini Gem Development | 160 hrs (80 + 80) | System Architect + QA Lead | Weeks 3–4 |
| Phase 3 — Validation & Launch | 120 hrs (60 + 60) | Project Manager + UX Designer | Weeks 5–6 |
| Total | 360 hrs | ~2.5 FTE Average | 6 Weeks |

Note: AI-assisted development using Claude Pro, Gemini, and open-source frameworks (CrewAI, LangGraph) can significantly improve productivity and reduce manual effort.

## 6.7 Risk Mitigation for Compressed Timeline

| Risk | Mitigation Strategy |
| --- | --- |
| Scope Creep | Strictly enforce "one job, one user" — focus exclusively on the Nenu Evaru? Gemini Gem MVP |
| Prompt Quality Issues | Conduct iterative testing with 10–15 users during Week 5 and refine prompts based on real-world feedback |
| Technical Debt | Build a modular architecture and document technical decisions to support future scalability |
| Team Burnout | Maintain sustainable 40-hour work weeks and leverage AI-assisted development (Claude Pro, Gemini) to reduce manual effort |

### Key Takeaway

A lean team, tight MVP scope, and AI-assisted development workflow make it realistic to deliver a functional and validated "Nenu Evaru?" Gemini Gem within 6 weeks, while maintaining quality and minimizing development risk.

## SECTION 7: BUDGET & RESOURCES

### 7.1 Global AI Agent Development Market Context

The global AI Agent market is experiencing rapid growth, driven by advancements in generative AI, autonomous agents, and enterprise AI adoption.

| Metric | Market Size |
| --- | --- |
| Global AI Agent Market (2024) | USD 5.09 Billion |
| Global AI Agent Market (2031 Forecast) | USD 10.23 Billion |
| CAGR (2025–2031) | 11.7% |

Source: QY Research – Global AI Agent Market Report (2025–2031)**.

### 7.2 Indian AI Development Context

| Metric | Value | Source |
| --- | --- | --- |
| Indian IT & ITeS Workforce | 5.8M+ professionals | NASSCOM (2025) |
| Career Guidance Market (India, 2025) | USD 2.86 Billion | Industry Projection |
| Career Counseling Market Growth (CAGR) | 7%+ | Industry Projection |

Source: NASSCOM 2025, Industry Reports & Market Projections.

### 7.3 Gemini API Pricing (Official — Google, 2025)

| Model | Input Cost (≤200k ctx) | Output Cost (≤200k ctx) | Best Use Case |
| --- | --- | --- | --- |
| Gemini 2.5 Flash | $0.10 per 1M tokens | $0.40 per 1M tokens | Fast, cost-effective — recommended |
| Gemini 2.5 Flash-Lite | $0.10 per 1M tokens | $0.40 per 1M tokens | Lowest-cost option |
| Gemini 2.5 Pro | $1.25 per 1M tokens | $10.00 per 1M tokens | Complex reasoning, synthesis |

Key Insight: Gemini 2.5 Flash-Lite is Google's fastest and lowest-cost model (0.10 input /0.40 output per 1M tokens), offering a 1 million-token context window and optional reasoning capabilities.

Source: Google Gemini API Pricing

### 7.4 AI Agent Development Costs (2026 Market Data)

| Tier | Cost Range (USD) | Cost Range (INR) | Features | Timeline | Source |
| --- | --- | --- | --- | --- | --- |
| Lightweight / MVP | 7,000–15,000 | ₹5.95L–₹12.75L | Single-scenario, basic memory, 1–2 API calls | 1–2 months | Industry Benchmark |
| Intermediate | 25,000–60,000 | ₹21.25L–₹51L | Multi-step workflows, DB integration | 3–5 months | Industry Benchmark |
| Enterprise | $100,000+ | ₹85L+ | Multiple specialist agents, security compliance | 6+ months | Industry Benchmark |

Note: INR conversion assumed at approximately ₹85/USD.

### 7.5 Career Guidance Website Cost Benchmarks (Indian Context)

| Region | Cost Range | Build Time | Features Included | Source |
| --- | --- | --- | --- | --- |
| USA | 1,000–5,900 | 3–10 weeks | Assessments, booking, AI chatbot, CRM | Industry Benchmark |
| India | ₹1.5L–₹7.5L (1,800–9,000) | 3–8 weeks | Career assessments, booking, personalization | Industry Benchmark |

Source: Industry benchmarks for educational and career guidance platforms.

### 7.6 Baagupadu Budget — Using AI Agents & Agentic Workflows

Note on Currency: INR conversion assumed at approximately ₹85/USD.

| Category | Tool / Service | Monthly Cost (INR) | Monthly Cost (USD) | Notes |
| --- | --- | --- | --- | --- |
| AI Models | Gemini 2.5 Flash-Lite | ₹8–₹34 | 0.10–0.40 per 1M tokens | Free tier covers initial development |
| Orchestration | CrewAI / LangGraph | ₹0 | $0 | Open-source frameworks |
| Frontend | Vercel / Cloudflare | ₹0–₹850 | 0–10 | Free tier until scaling |
| Backend | Node.js / Python | ₹0 | $0 | Self-hosted, open-source |
| Database | PostgreSQL / SQLite | ₹0 | $0 | Local/light cloud |
| AI Development Tools | ChatGPT / Claude Pro | ₹1,700–₹2,550 | 20–30 | Prompt engineering & testing |
| Total Monthly |  | ₹1,700–₹3,400 | 20–40 |  |

### One-Time Build Cost (India Context)

- Industry benchmark for lightweight AI agent MVP: 7,000–15,000 (~₹5.95L–₹12.75L)

- IIT Mandi iHub AI Agent Course Fee: ₹49,999 (inclusive of GST, accommodation, and meals)

- Total Estimated Investment: ~₹6L–₹13L (7,000–15,000)

Sources: Industry Benchmarks, Google Gemini Pricing, IIT Mandi iHub AI Programs.

### 7.7 Cost-Saving Strategies for Indian Context

| Strategy | Implementation | Potential Savings |
| --- | --- | --- |
| NCS Portal Integration | Leverage government career guidance platform | Significant development cost reduction |
| Open-source AI Frameworks | Use CrewAI, LangGraph instead of proprietary solutions | ₹5L–₹15L |
| Free Tiers | Utilize Gemini API Free Tier, Vercel Free, and Cloudflare Free plans | Up to 50% reduction in infrastructure costs |
| Student / Bootstrapped Team | Leverage India's large pool of engineering and AI talent | Lower personnel and operational costs |

Key Insight: By combining government resources (e.g., NCS), open-source AI frameworks, and free cloud tiers, startups can reduce initial development and infrastructure expenses substantially while maintaining scalability.

Sources: National Career Service (NCS), Google Gemini API Pricing, CrewAI Documentation, LangGraph Documentation, Vercel Pricing, Cloudflare Pricing.

### 7.8 Realistic Revenue Projections for an Unlaunched Indian Startup

### Guiding Philosophy

Revenue projections for a pre-launch startup should reflect realistic, gradual growth. While "hockey-stick" growth curves are common in pitch decks, they are rarely achieved by early-stage startups without significant capital, partnerships, and sustained market traction.

### The Challenge: Realistic EdTech Startup Growth

Industry data shows that even well-funded edtech companies require years to scale revenues.

For example, UNIVO Education, after raising USD 76.6 million in Series-A funding, required several years to build and scale its business model. Similarly, CL Educate Limited, a publicly listed Indian education company, demonstrated gradual and sustainable growth rather than exponential revenue expansion.

| Fiscal Year | Revenue from EdTech (INR) | Revenue from EdTech (USD) |
| --- | --- | --- |
| FY 2025 | ₹193 Crore | ~$23M |
| FY 2024 | ₹176 Crore | ~$21M |
| FY 2023 | ₹131 Crore | ~$15.7M |
| FY 2022 | ₹107 Crore | ~$12.8M |

Source: Stock Analysis (based on CL Educate financial filings)

Key Insight: CL Educate increased its EdTech revenue from ~12.8M to ~23M over four years, corresponding to a 13.6% CAGR—a realistic and sustainable growth trajectory rather than a hockey-stick curve.

### Real-World Indian Market Benchmarks

- EzLearn follows a subscription model starting at ₹665 for 6 months, targeting affordability for Indian students.

- Ohual.ai, an AI-powered career guidance platform, offers micro-subscriptions starting at ₹50/month, emphasizing accessibility and scale.

These examples demonstrate that the Indian market favors low-cost, high-value subscription models.

### Realistic Revenue Forecast — Baagupadu (Year 1 to Year 3)

| Metric | Year 1 | Year 2 | Year 3 | Reasoning |
| --- | --- | --- | --- | --- |
| Pricing Model | Freemium / Low-cost Entry | Monthly Subscription | Tiered Subscription | Based on EzLearn & Ohual models |
| Average Revenue per User (ARPU) | ₹25–₹100 (0.30–1.20) | ₹100–₹300 (1.20–3.50) | ₹300–₹500 (3.50–6) | Gradual premium adoption |
| Monthly Subscription | ₹49/month | ₹99–₹199/month | ₹299–₹499/month | Affordable pricing for Indian users |
| Active Users | 500–1,000 | 2,000–5,000 | 5,000–10,000 | Growth via referrals, NCS integration, and college partnerships |
| Annual Revenue | ₹1.5L–₹6L (1,800–7,200) | ₹12L–₹60L (14,400–72,000) | ₹60L–₹2Cr (72,000–240,000) | Based on EdTech industry benchmarks |
| Revenue Growth | — | 10×–20× | 5×–10× | Product-market fit and network effects |

### Revenue Projections — Scenario Analysis

| Scenario | Year 1 (INR) | Year 2 (INR) | Year 3 (INR) | Conditions |
| --- | --- | --- | --- | --- |
| Conservative | ₹1.5L ($1,800) | ₹12L ($14,400) | ₹60L ($72,000) | Slow adoption, limited marketing, ~500 users in Year 1 |
| Moderate | ₹3L ($3,600) | ₹30L ($36,000) | ₹1.2Cr ($144,000) | Referral growth, NCS partnership, ~1,000 users in Year 1 |
| Optimistic | ₹6L ($7,200) | ₹60L ($72,000) | ₹2Cr ($240,000) | Strong product-market fit, college partnerships, 2,000+ users in Year 1 |

### Key Assumptions & Reasoning

- Indian Market Affordability

  - Indian students and young professionals are highly price-sensitive.

  - Pricing is aligned with platforms such as EzLearn (₹665/6 months) and Ohual.ai (₹50/month).

- Freemium-to-Premium Conversion

  - Early users are expected to adopt free or low-cost plans.

  - Premium conversion rates in Indian EdTech typically range between 5–15%.

- Gradual ARPU Growth

  - Revenue per user increases as users perceive value and upgrade to premium offerings.

- Customer Acquisition Cost (CAC) vs Lifetime Value (LTV)

  - Referral-driven growth and institutional partnerships help maintain a low CAC while increasing LTV.

- NCS Portal Partnership

  - The National Career Service (NCS) ecosystem, with 4.85 crore+ active employers and 4 crore+ active vacancies, represents a significant opportunity for accelerating adoption.

- Market Growth Context

  - Global AI Career Coach Market: 5.48B (2025) →14.82B (2030) at 22% CAGR

  - India's Career Counseling Market: $2.86B (2025) with 7%+ CAGR

  - India's youth population: 600M+ individuals under 35

### Revenue Timeline (Moderate Scenario)

text

Year 1 (Funding & Launch)


├── Months 1-6 : Build MVP and launch Gemini Gem


├── Months 7-12: Freemium adoption (500-1,000 users)


└── Revenue: ~₹3L (~$3,600)


 

Year 2 (Early Growth)


├── Months 13-18: Referral growth and NCS integration


├── Months 19-24: College partnerships (2,000-5,000 users)


└── Revenue: ~₹30L (~$36,000)


 

Year 3 (Scale)


├── Months 25-30: Product-market fit and premium subscriptions


├── Months 31-36: Institutional partnerships (5,000-10,000 users)


└── Revenue: ~₹1.2Cr (~$144,000)

### Critical Success Factors

- Strong Partnerships: NCS integration, college collaborations, and industry partnerships are crucial for accelerating user acquisition.

- Product-Market Fit: The platform must deliver tangible value through effective personality-based guidance to drive conversions.

- Affordable Pricing: Aligning with Indian market expectations for value-based, low-cost solutions.

- Freemium Model: Leveraging free access to build a large user base before converting to premium offerings.

- Brand Trust: Building credibility through transparency, accuracy, and positive user outcomes.

Sources: National Career Service (NCS) Data, EzLearn Pricing, Ohual.ai Pricing, Indian EdTech Market Reports, CL Educate Financial Analysis.

### 7.9 Funding Context

For reference, several Indian AI-powered career guidance startups are actively raising capital and adopting sustainable growth strategies:

- AapkaMentor.ai is seeking 500K–1M in pre-seed funding with a goal of reaching 50,000 users within 18 months.

- Ohual.ai operates in the Indian market using a micro-subscription model starting at ₹50/month, emphasizing affordability and accessibility.

- EzLearn follows a low-cost, high-value subscription model, offering plans starting at ₹665 for 6 months.

### Key Takeaways

These benchmarks indicate that:

- Early-stage Indian AI startups typically raise modest amounts of capital, especially during pre-seed and seed stages.

- Revenue growth is gradual and requires time, particularly in India's price-sensitive education market.

- Sustainable growth is often driven by referrals, partnerships, and community engagement, rather than aggressive marketing expenditure.

### 7.10 References (Section-Wise)

| Source | Citation / Link | Key Finding |
| --- | --- | --- |
| Stock Analysis / CL Educate | CL Educate Annual Reports | EdTech revenue: ₹193Cr (FY25), ₹176Cr (FY24), ₹131Cr (FY23), ₹107Cr (FY22) |
| StartinUP / EzLearn | EzLearn Pricing & Business Model | Subscription model: ₹665 / 6 months, ₹99/month premium |
| Ohual.ai (LinkedIn) | Company Profile & Updates | Micro-subscription model starting at ₹50/month; operating in India |
| Research and Markets | AI Career Coach Market Report | Global market: 5.48B (2025) →14.82B (2030) at 22% CAGR |
| PIB / National Career Service (NCS) | Government Statistics | NCS Portal: 4.85Cr+ active employers and 4.0Cr+ active vacancies |
| Prezi / AapkaMentor.ai | Startup Pitch / Company Presentation | Seeking 500K–1M pre-seed funding; target of 50,000 users in 18 months |
| Campus Binge (LinkedIn) | Career Counseling Market Insights | Indian career counseling market valued at $2.86B (2025) with 7%+ CAGR |
| Financial Express / UNIVO | Funding & Growth Reports | 7× revenue growth; $76.6M Series-A funding; "low-burn, high-scale" strategy |

### Summary

The Indian AI-powered career guidance ecosystem is still in its early stages, characterized by:

- Affordable subscription models (₹50–₹199/month)

- Modest early-stage funding rounds (500K–1M)

- Referral and partnership-led growth

- Strong market potential, supported by India's large youth population, growing digital adoption, and increasing demand for personalized career guidance.

These trends position Baagupadu to pursue a sustainable, low-burn growth strategy focused on accessibility, affordability, and long-term user engagement.

## SECTION 8: RISK MANAGEMENT (Revised — 6-Week Horizon)

### 8.1 Guiding Philosophy: Immediate Risk Focus

With a 6-week timeline, risk management shifts from long-term strategic planning to immediate execution risks. The focus is on identifying what could derail the launch and implementing mitigation strategies that can be executed within days rather than months.

Key Principle: In a compressed timeline, prevention is cheaper than recovery. Every day lost to an unmanaged risk threatens the entire launch window.

### 8.2 Risk Summary Dashboard

| Priority | Risk ID | Risk |
| --- | --- | --- |
| 🔴 HIGH | BGP-RSK-001 | Prompt Quality & Personality Inconsistency |
| 🔴 HIGH | BGP-RSK-002 | Technical Integration Failures |
| 🔴 HIGH | BGP-RSK-003 | Insufficient User Testing Feedback |
| 🟡 MEDIUM | BGP-RSK-004 | Team Availability & Burnout |
| 🟡 MEDIUM | BGP-RSK-005 | Scope Creep |
| 🟢 LOW | BGP-RSK-006 | API Cost Overrun |
| 🟢 LOW | BGP-RSK-007 | Competitor Activity |

### 8.3 Detailed Risk Register

#### Risk 1: Prompt Quality & Personality Inconsistency

| Field | Value |
| --- | --- |
| Risk ID | BGP-RSK-001 |
| Category | Product / Quality Risk |
| Probability | HIGH (75%) |
| Impact | CRITICAL (5/5) |
| Priority Score | 3.75 |
| Risk Owner | Prompt Engineer |
| Response Owner | AI Product Architect |

### Problem Statement

Sahayam's personality may become inconsistent across the six phases, or prompts may fail to create the intended conversational experience. Users may feel they are interacting with a robot instead of a trusted companion.

### Implications

| Implication | Impact | Timeline |
| --- | --- | --- |
| User feels like taking a survey | Critical | Week 1–2 |
| Loss of trust in Sahayam | Critical | Immediate |
| Low completion rate (<50%) | High | Week 5 |
| Negative user feedback | High | Week 5–6 |

### Mitigation Strategies

| Strategy | Owner | Timeline | Success Criteria |
| --- | --- | --- | --- |
| Create Sahayam Personality Guide | Prompt Engineer | Week 1 | Personality documented |
| Single owner for prompt edits | AI Product Architect | Week 1–2 | Consistency maintained |
| Daily prompt reviews | Prompt Engineer + UX Designer | Week 1–2 | All prompts reviewed |
| Internal testing with 2–3 users | QA Lead | Week 3 | Feels conversational |

### Contingency Plan

- Dedicate 2 additional days for prompt rewriting.

- Create a Sahayam voice cheat-sheet.

- Rewrite robotic questions using storytelling formats such as:

  - "Imagine..."

  - "Remember when..."

#### Risk 2: Technical Integration Failures

| Field | Value |
| --- | --- |
| Risk ID | BGP-RSK-002 |
| Category | Technical Risk |
| Probability | MEDIUM (50%) |
| Impact | CRITICAL (5/5) |
| Priority Score | 2.50 |
| Risk Owner | System Architect |
| Response Owner | System Architect + QA Lead |

### Problem Statement

The Gemini Gem may fail to integrate system prompts, question banks, or frameworks correctly. Context window limitations may cause memory loss across phases.

### Implications

| Implication | Impact | Timeline |
| --- | --- | --- |
| Gem crashes | Critical | Week 4 |
| Memory loss | High | Week 4 |
| Delayed launch | Critical | Week 6 |
| User frustration | High | Week 5–6 |

### Mitigation Strategies

| Strategy | Owner | Timeline |
| --- | --- | --- |
| Modular architecture | System Architect | Week 3 |
| Phase-wise testing | QA Lead | Week 4 |
| Context window monitoring | System Architect | Week 4 |
| Early integration testing | System Architect | Week 3 |

### Contingency Plan

- Dedicate 2 days to debugging.

- Compress prompts and simplify language.

- Roll back to individual phase testing if integration fails.

#### Risk 3: Insufficient User Testing Feedback

| Field | Value |
| --- | --- |
| Risk ID | BGP-RSK-003 |
| Category | Validation Risk |
| Probability | MEDIUM (50%) |
| Impact | HIGH (4/5) |
| Priority Score | 2.00 |
| Risk Owner | Project Manager |
| Response Owner | UX Designer + Project Manager |

### Problem Statement

A small sample size or incomplete journeys may leave important usability issues undiscovered.

### Mitigation Strategies

| Strategy | Owner | Timeline |
| --- | --- | --- |
| Recruit 15–20 users | Project Manager | Week 5 |
| Offer ₹100–₹200 incentives | Project Manager | Week 5 |
| Keep sessions short (15 min) | UX Designer | Week 5 |
| Use surveys + interviews | UX Designer | Week 5 |

### Contingency Plan

- Extend testing by 2 days.

- Conduct follow-up interviews.

- Focus on completed phases if users drop off.

#### Risk 4: Team Availability & Burnout

| Field | Value |
| --- | --- |
| Risk ID | BGP-RSK-004 |
| Category | Operational Risk |
| Probability | HIGH (60%) |
| Impact | HIGH (4/5) |
| Priority Score | 2.40 |

### Mitigation Strategies

| Strategy | Owner |
| --- | --- |
| Define clear roles (RACI) | Project Manager |
| Weekly workload check-ins | Project Manager |
| Use AI-assisted development | Entire Team |
| Add schedule buffers | Project Manager |

### Contingency Plan

- Add 2–3 buffer days.

- Reduce non-essential scope.

- Cross-train or outsource if necessary.

#### Risk 5: Scope Creep

| Field | Value |
| --- | --- |
| Risk ID | BGP-RSK-005 |
| Category | Scope Risk |
| Probability | MEDIUM (50%) |
| Impact | HIGH (4/5) |
| Priority Score | 2.00 |

### Mitigation Strategies

| Strategy | Owner |
| --- | --- |
| Enforce "One Job, One User" | AI Product Architect |
| Maintain feature backlog | Project Manager |
| Feature freeze after Week 3 | Product Team |
| Prioritization matrix | AI Product Architect |

### Contingency Plan

- Freeze all new features after Week 3.

- Defer additions to Version 2.

#### Risk 6: API Cost Overrun

| Field | Value |
| --- | --- |
| Risk ID | BGP-RSK-006 |
| Category | Financial Risk |
| Probability | LOW (20%) |
| Impact | MEDIUM (3/5) |
| Priority Score | 0.60 |

### Mitigation Strategies

| Strategy | Owner |
| --- | --- |
| Monitor API usage daily | System Architect |
| Use Gemini 2.5 Flash-Lite | System Architect |
| Compress prompts | Prompt Engineer |
| Cache common responses | System Architect |

#### Risk 7: Competitor Activity

| Field | Value |
| --- | --- |
| Risk ID | BGP-RSK-007 |
| Category | Market Risk |
| Probability | LOW (15%) |
| Impact | LOW (2/5) |
| Priority Score | 0.30 |

### Mitigation Strategies

| Strategy | Owner |
| --- | --- |
| Focus on differentiation | AI Product Architect |
| Launch quickly | Project Manager |
| Monitor competitors | Project Manager |

### Key Differentiator

Life-stage pattern recognition + empathetic AI conversations remain Baagupadu's unique advantage over generic career guidance tools.

### 8.4 Risk Response Timeline (6-Week Horizon)

text

┌───────────────────────────────────────────────────────────────┐


│                 RISK RESPONSE TIMELINE                        │


├───────────────────────────────────────────────────────────────┤


 

WEEK 1-2: FOUNDATION RISKS


├── BGP-RSK-001: Prompt Quality & Personality Inconsistency


│   └── Create Personality Guide; daily peer reviews


│


├── BGP-RSK-004: Team Availability & Burnout


│   └── Clear role definitions; weekly check-ins


│


└── BGP-RSK-005: Scope Creep


    └── Feature prioritization; enforce


        "one job, one user"


 

───────────────────────────────────────────────────────────────


 

WEEK 3-4: DEVELOPMENT RISKS


├── BGP-RSK-002: Technical Integration Failures


│   └── Modular architecture; early integration testing


│


├── BGP-RSK-006: API Cost Overrun


│   └── Daily monitoring; use Gemini 2.5 Flash-Lite


│


└── BGP-RSK-004: Team Availability & Burnout


    └── Monitor workload; use buffer days


 

───────────────────────────────────────────────────────────────


 

WEEK 5-6: VALIDATION & LAUNCH RISKS


├── BGP-RSK-003: Insufficient User Testing Feedback


│   └── Over-recruit; offer incentives;


│       multiple feedback methods


│


├── BGP-RSK-001: Prompt Quality


│   └── Final refinements based on user feedback


│


└── BGP-RSK-007: Competitor Activity


    └── Monitor competitors; accelerate launch if required


 

└───────────────────────────────────────────────────────────────┘

### 8.5 Risk Governance

| Element | Details |
| --- | --- |
| Risk Review Cadence | Daily 15-minute stand-up + Weekly comprehensive risk review |
| Risk Escalation Protocol | Critical Risks: Escalate within 24 hours; High Risks: Escalate within 48 hours |
| Risk Owner Accountability | Weekly progress report submitted to the Project Manager |
| Reporting Mechanism | Weekly Risk Dashboard using Green / Yellow / Red status indicators |

### 8.6 Risk Summary Table (6-Week Horizon)

| Risk ID | Risk | Probability | Impact | Priority Score | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- |
| BGP-RSK-001 | Prompt Quality & Personality Inconsistency | HIGH (75%) | CRITICAL | 3.75 | Prompt Engineer | 🟢 |
| BGP-RSK-002 | Technical Integration Failures | MEDIUM (50%) | CRITICAL | 2.50 | System Architect | 🟢 |
| BGP-RSK-003 | Insufficient User Testing Feedback | MEDIUM (50%) | HIGH | 2.00 | Project Manager | 🟢 |
| BGP-RSK-004 | Team Availability & Burnout | HIGH (60%) | HIGH | 2.40 | Project Manager | 🟡 |
| BGP-RSK-005 | Scope Creep | MEDIUM (50%) | HIGH | 2.00 | AI Product Architect | 🟢 |
| BGP-RSK-006 | API Cost Overrun | LOW (20%) | MEDIUM | 0.60 | Project Manager | 🟢 |
| BGP-RSK-007 | Competitor Activity | LOW (15%) | LOW | 0.30 | Project Manager | 🟢 |

### Key Takeaway

The highest-priority risks for the 6-week Baagupadu MVP timeline are:

- Prompt Quality & Personality Consistency (BGP-RSK-001)

- Technical Integration Failures (BGP-RSK-002)

- User Testing Feedback Quality (BGP-RSK-003)

By maintaining a tight MVP scope, leveraging AI-assisted development, and conducting early testing, the team can significantly reduce execution risks and improve the likelihood of a successful launch.

## SECTION 9: SUCCESS CRITERIA & KPIs (Revised — 6-Week Horizon)

### 9.1 Guiding Philosophy: Launch-Focused Metrics

With a 6-week timeline, success is measured by what is delivered at launch rather than long-term growth. The focus is on product quality, user validation, and readiness for post-launch iteration.

Key Principle: The goal is to launch a functional, tested product—not to achieve perfect market fit in 6 weeks. Market fit comes later through iteration and user feedback.

### 9.2 Primary Success Metrics (Launch-Focused)

| Metric | Target | Measurement Method | Owner | When Measured |
| --- | --- | --- | --- | --- |
| Deliverable Completion Rate | 100% of planned deliverables | Project tracking | Project Manager | Week 6 |
| Technical Quality | Zero critical bugs at launch | QA testing | QA Lead | Week 6 |
| User Satisfaction | >4.0 / 5 | Post-test survey (10–15 users) | UX Designer | Week 6 |
| Completion Rate (Testing) | >80% users complete all 6 phases | Analytics | UX Designer | Week 6 |
| Launch Readiness | All launch checklist items complete | Launch checklist | Project Manager | Week 6 |
| API Cost (Testing) | <$50 total (within free tier) | API usage monitoring | System Architect | Week 6 |

### 9.3 Secondary Success Metrics (Post-Launch Indicators)

| Metric | Target | Measurement Method | Owner | When Measured |
| --- | --- | --- | --- | --- |
| User Feedback Quality | Actionable insights from >80% testers | Feedback analysis | UX Designer | Week 6 |
| Phase Transition Smoothness | Natural transitions reported by users | User survey | UX Designer | Week 6 |
| Persona Accuracy | >70% users agree with persona | User validation | AI Product Architect | Week 6 |
| Guidance Quality | >70% users find guidance useful | User survey | Career Architect | Week 6 |
| Sahayam Personality Consistency | Users describe Sahayam consistently | Open-ended feedback | Prompt Engineer | Week 6 |

### 9.4 Phase Success Criteria

## Phase 1 — Foundation (Weeks 1–2)

| Success Criteria | Verification Method | Owner |
| --- | --- | --- |
| system_prompt.md v1.0 complete | Document review | Prompt Engineer |
| All 3 question banks complete | File verification | Conversational Designer |
| Personality consistency documented | Style Guide review | UX Designer |
| All 6 phases designed | Phase transition logic review | AI Product Architect |
| Internal review complete | Review sign-off | AI Product Architect |

### Success Metrics

- All 6 phases designed with natural transitions

- 45+ childhood questions created

- 45+ teenage questions created

- 15+ adult questions created

- Personality Style Guide completed

- Phase transition language defined

## Phase 2 — Gemini Gem Development (Weeks 3–4)

| Success Criteria | Verification Method | Owner |
| --- | --- | --- |
| Working Gemini Gem (M1) | Functional testing | System Architect |
| All prompts integrated | Integration testing | System Architect |
| All question banks integrated | Integration testing | System Architect |
| All frameworks integrated | Integration testing | System Architect |
| No critical bugs | QA testing | QA Lead |
| Phase transitions are natural | Internal testing | UX Designer |

### Success Metrics

- M1: Working Gemini Gem completed by Week 4

- Zero critical bugs (system crash, data loss)

- All 6 phases functional

- Sahayam personality consistent across phases

- Natural phase transitions

## Phase 3 — Validation & Launch (Weeks 5–6)

| Success Criteria | Verification Method | Owner |
| --- | --- | --- |
| 10–15 users tested | User testing data | Project Manager |
| >80% completion rate | Analytics | UX Designer |
| User satisfaction >4.0/5 | Survey | UX Designer |
| All critical issues fixed | QA testing | QA Lead |
| Launch checklist complete | Launch review | Project Manager |
| M2: Validation & Launch Complete | Sign-off | AI Product Architect |

### Success Metrics

- 10–15 users complete all phases

80% completion rate during testing

- User satisfaction >4.0/5

- Zero critical bugs remaining

- All launch checklist items complete

- M2: Validation & Launch Complete by Week 6

### 9.5 Quality Gates (Go / No-Go Decision Points)

| Gate | Decision Point | Criteria | Owner | Consequence |
| --- | --- | --- | --- | --- |
| Gate 1 | End of Week 2 | All Phase 1 deliverables complete | AI Product Architect | Go: Proceed to Phase 2<br>No-Go: Add 1 week for refinements |
| Gate 2 | End of Week 4 | Working Gemini Gem (M1) with no critical bugs | System Architect | Go: Proceed to Phase 3<br>No-Go: Delay testing by 2 days |
| Gate 3 | End of Week 6 | All launch criteria met | AI Product Architect | Go: Launch<br>No-Go: Postpone launch by 1 week |

### 9.6 Post-Launch Success Indicators (Future Monitoring)

| Metric | Year 1 Target | Measurement Method | Owner |
| --- | --- | --- | --- |
| Active Users (Month 1 Post-Launch) | 100+ | Analytics | Project Manager |
| User Return Rate (30 Days) | >30% | Analytics | UX Designer |
| Conversation Completion Rate | >70% | Analytics | AI Product Architect |
| Net Promoter Score (NPS) | >6 / 10 | Survey | Project Manager |
| Monthly API Cost | <$50 | API Monitoring | System Architect |

### Key Takeaway

The success of the "Nenu Evaru?" Gemini Gem MVP is defined by:

- Launching a functional and stable Gemini Gem within 6 weeks

- Achieving high user satisfaction (>4.0/5)

- Ensuring >80% completion of the six-phase journey

- Maintaining Sahayam's personality consistency

- Building a strong foundation for post-launch iteration and growth

## SECTION 10: GOVERNANCE & COMMUNICATION

### 10.1 Stakeholder Communication Matrix

| Stakeholder | Information Need | Frequency | Channel | Owner |
| --- | --- | --- | --- | --- |
| Executive Board | Strategic progress | Monthly | Board Presentation | Vision Holder |
| Investment Partners | Financial metrics | Quarterly | Investor Report | Project Manager |
| Project Team | Daily progress | Daily | Slack / Email | Project Manager |
| Extended Team | Weekly updates | Weekly | Weekly Meeting | Project Manager |
| Early Testers | Product feedback | Weekly | Feedback Form | UX Designer |

### 10.2 Meeting Cadence

| Meeting | Duration | Attendees | Purpose | Owner |
| --- | --- | --- | --- | --- |
| Daily Stand-Up | 15 min | Core Team | Progress, blockers, next steps | Project Manager |
| Weekly Sync | 60 min | Core + Extended Team | Progress review, decisions, alignment | Project Manager |
| Monthly Review | 90 min | Executive + Core Team | Strategic review, milestones, risks | Vision Holder |

### 10.3 Reporting Schedule

| Report | Format | Content | Owner |
| --- | --- | --- | --- |
| Daily Status | Slack / Email | What was done, blockers | All team members |
| Weekly Dashboard | Sheet / PDF | Progress, metrics, risks | Project Manager |
| Monthly Executive Report | Slide deck / PDF | Strategic updates, financials, milestones | Vision Holder & Project Manager |

### 10.4 Escalation Protocol

┌─────────────────────────────────────────────────────────────────┐


│  LEVEL 1 — Team Lead (24–48 hrs)                                  │


│   Issue identified → Team Lead attempts resolution                 │


│   If unresolved → escalate to Level 2                              │


│                                                                   │


│  LEVEL 2 — Project Manager (48–72 hrs)                             │


│   Coordinates resolution, involves relevant stakeholders           │


│   If unresolved → escalate to Level 3                              │


│                                                                   │


│  LEVEL 3 — Project Vision Holder (72+ hrs)                         │


│   Final decision maker — no further escalation                     │


└─────────────────────────────────────────────────────────────────┘

### 10.5 Quality Assurance Approach

| Testing Level | Who | When | Success Criteria |
| --- | --- | --- | --- |
| Unit Testing (Prompt Level) | Prompt Engineer | Phase 1 | All prompts pass validation |
| Integration Testing (Gem + Website) | System Architect | Phase 3 | All APIs work correctly |
| User Acceptance Testing (UAT) | Project Manager + UX Designer | Phases 2 & 3 | User satisfaction >4.0/5 |
| Performance Testing (Load & Speed) | System Architect | Phase 3 | <3s response, <5% error rate |

Bug Severity & Response SLA

| Severity | Definition | Response Time |
| --- | --- | --- |
| 🔴 Critical | System crash, data loss | 24 hours |
| 🟡 High | Major feature broken | 48 hours |
| 🟢 Medium | Minor issue | 1 week |
| ⚪ Low | Cosmetic issue | 2 weeks |

## SECTION 11: APPROVAL SECTION

I acknowledge that I have reviewed the Baagupadu Project Charter (Version 1.0) and agree with its contents. This document authorizes the project team to proceed with Phase 1: Foundation.

| Role | Signature | Date |
| --- | --- | --- |
| Project Vision Holder | _______________________ | __________ |
| Executive Sponsor | _______________________ | __________ |
| AI Product Architect | _______________________ | __________ |
| System Architect | _______________________ | __________ |
| Project Manager | _______________________ | __________ |
| Lead Investor | _______________________ | __________ |

## APPENDICES

### Appendix A: Glossary

| Term | Definition |
| --- | --- |
| Baagupadu | AI-powered mentoring ecosystem (Telugu: "Who Am I?") |
| Sahayam | AI mentor personality (Sanskrit/Telugu: "Companion") |
| Nenu Evaru? | First Gemini Gem (Telugu: "Who Am I?") |
| Persona | Synthesized understanding of who the user is |
| Traits | Specific characteristics identified through pattern recognition |
| Life Stages | Childhood (0–12), Teenage (13–19), Adult (20–30) |
| Gemini Gem | Specialized AI application built within Google Gemini |

### Appendix B: Reference Documents

| Document | Description |
| --- | --- |
| Learning_Pal_Concept_Documentation | Original concept documentation |
| system_prompt.md | Sahayam's personality and behavior definition |
| trait_framework.json | Trait identification system |
| persona_framework.json | Persona synthesis framework |
| career_framework.json | Career guidance framework |

End of Document — Baagupadu Project Charter v1.0